| Meeting Title: | Process Implementation Approach – Finalization |  |
| --- | --- | --- |
| Date: | 28-Feb-2012 |  |
| Place: | Conference room |  |
| Bridge Information: | Follow up of meeting with Venu on 16-Feb-2012 |  |
| Chair Person: |  |  |
| Invitee List: | Internal: | Raja, Gopu, Chinnappa, Sridhar, Hari |
|  | External: |  |
| In Attendance: | Internal: | Raja, Gopu, Chinnappa, Sridhar, Hari |
|  | External: |  |
| Absent: | Internal: | Nicholas |
|  | External: |  |
| Agenda: | To put forth the short term and long term objectives of the committee. |  |
| Minutes Submitted By: | Hari |  |
| Minutes Submitted On: | 28-Feb-2012 |  |
| Next Meeting: | Date: | 29-Feb-2012 |
|  | Time: |  |
|  | Place: |  |
|  | Bridge: |  |
|  | Chair: |  |

### Decisions:

| # | Decision |
| --- | --- |
|  | To organize meeting with individual teams and identify the problems in Client Delivery Process. |
|  | To prepare a questionnaire based on the team meetings conducted. |
|  | To conduct an online survey. |

### Action Items:

| # | Action Item | Owner | Status | Due Date | Comments |
| --- | --- | --- | --- | --- | --- |
|  | Schedule meeting with teams | Gopu | Yet to start | 29-Feb-2012 |  |
|  | Prepare questionnaire | Committee members | Yet to start | 30-Feb-2012 |  |
|  | Publish survey in ADMS | Chinnappa | Yet to start | 30-Feb-2012 |  |

### Carry-Over Items for Next Meeting:

| # | Description |
| --- | --- |
|  | To set deadline for consolidating survey. |
|  | To set deadline for defining delivery process. |
|  | To communicate delivery process to individual teams. |

### Notes:

To know about delivery related documents from all the teams.